## Arkusz1
KW | from | to | to do | Bartek | Stergios
9 | 2021-03-01 | 2021-03-07 | SEIR Model working, first draft of an agent based model
10 | 2021-03-08 | 2021-03-14 | continue working on agent based model
11 | 2021-03-15 | 2021-03-21 | SEIR agent based model ready, evaluation with supervisors
12 | 2021-03-22 | 2021-03-28 | Starting with reinforcemnt learning, literature etc, possible work for agent based model correction
13 | 2021-03-29 | 2021-04-04 | Continue working on reinforcement learning, final version of agent based model ready
14 | 2021-04-05 | 2021-04-11 | First draft of reinforcement learning application
15 | 2021-04-12 | 2021-04-18 | Improvements / Corrections of reinforcement learning
16 | 2021-04-19 | 2021-04-25 | Final version of reinforcemnet learning application to the model
17 | 2021-04-26 | 2021-05-02 | Start thesis writing / possible needed corrections to the model in general
18 | 2021-05-03 | 2021-05-09 | Writing thesis
19 | 2021-05-10 | 2021-05-16 | Writing thesis
20 | 2021-05-17 | 2021-05-23 | Writing thesis
21 | 2021-05-24 | 2021-05-30 | Writing thesis
22 | 2021-05-31 | 2021-06-03 | DEADLINE
`